[Insert Date]

[Name of Recipient]

[Principal Agent]

[Company Name]

[Street Address]

[City, Postal Code]

By email and registered post

Attention:  The Principal Agent

Dear Sir / Madam,

NOTICE OF DIRECTED ACCELERATION OF THE WORKS

On [date] you directed that we add labour, work extra shifts and work overtime (as applicable) to achieve completion of milestone(s) / activity number(s) [insert] on or before [date]. This is [number] working days / weeks / months prior to the scheduled completion of the relevant milestone, adjusted for excusable delays for which we are entitled to a revision of the date for practical completion.

The directive therefore constitutes a directed acceleration of the works because [cite reason — e.g. denial of the EOT to which we are entitled, or a unilateral instruction to advance completion].

We will endeavour to comply by increasing manpower and equipment as required. However, we hereby formally request additional compensation for all direct and indirect cost of the acceleration effort, including but not limited to: inefficiency from disruption, rescheduling, overmanning, stacking of trades, overtime, dilution of supervision and any other impact cost arising from the acceleration.

Once the cost of the accelerated effort can be quantified, a change order request will be prepared. Your cooperation in minimising the impact will be appreciated.

Yours faithfully,

________________________________

[Name of Signatory]

[Project Manager]

[Company Name]