[Insert Date]

[Name of Recipient]

[Main Contractor]

[Company Name]

[Street Address]

[City, Postal Code]

By email and registered post

Attention:  The Main Contractor

Dear Sir / Madam,

NOTICE OF INTENTION TO CLAIM REVISION OF THE SUBCONTRACT PRACTICAL COMPLETION DATE

We give notice in terms of the subcontract that an event has occurred which will, or is likely to, delay our subcontract practical completion. The event is [describe event], it commenced on [date] and we became aware of its delay-causing effect on [date].

This notice is issued in sufficient time to permit you to comply with your obligations under PBA Clause 23.4.2 (or any equivalent main-contract notice clause), being the 20 working-day notice period for the equivalent main-contract delay event.

A fully quantified subcontract claim will follow in accordance with the subcontract and any main-contract substantiation requirements passed down to us. Mitigation measures are being implemented and we will keep you advised of developments.

Yours faithfully,

________________________________

[Name of Signatory]

[Subcontract Project Manager]

[Company Name]